## SheetTemplate (hidden)
HAZOP STUDY WORKSHEET
Project: | [9 empty] | NODE
Design Intent : | [9 empty] | System
Design Conditions: | [9 empty] | HAZOP Boundary
Operating Conditions:
PFD, PID No. : | [9 empty] | Date
Guide Word | Deviation | Causes | Consequences | CAT | Unmitigated Risk Assessment Matrix |  |  | Major Accident Event | Existing Safeguards | Mitigated Risk Assessment Matrix |  |  | Recommendations | Action No. | Action by
|  |  |  | (P/A/E/R/Q) | S | L | R | (Y/N) |  | S | L | R
Note:

## Guide Word (hidden)
Guide Word + Paramter
Guide Word | Paramter | Deviations | Process Deviation (Examples of Cause) | Area of Application
Flow
No | Flow | No Flow | Incorrect routing – blockage – burst pipe – large leak – equipment failure (C.V., isolation valve, pump, vessel, etc.) – incorrect pressure differential – isolation in error – etc. | System
More of | Flow | More/High Flow | Increased pumping capacity – reduced delivery head – increased suction pressure – static generation under high velocity – pump gland leaks – etc. | System
Less of | Flow | Less/Low Flow | Line blockage– filter blockage – fouling in vessels – defective pumps – restrictor or orifice plates – etc. | System
Reverse | Flow | Reverse Flow | Incorrect pressure differential – two-way flow – emergency venting – incorrect operation – in-line spare equipment – etc. | System
Misdirected | Flow | Misdirected Flow | Flow directed to stream other than intended due to misalignment of valves – etc. | System
Pressure
More of | Pressure | More/High Pressure | Surge problems (line and flange sizes) – relief philosophy (process / fire etc.) – connection to high pressure system – gas breakthrough (inadequate venting) – defective isolation procedures for relief valves – thermal overpressure – positive displacement pumps – failed closed PCV's – design pressures – relief valve – specifications of pipes – vessels – fittings – instruments – type of relief device and reliability – discharge location – inlet-outlet piping – etc. | System
Less of | Pressure | Less/Low Pressure | Generation of vacuum condition – restricted pump/ compressor suction line – vessel drainage – etc. | System
Temperature
More of | Temperature | More/High Temperature | Ambient conditions – fire situation – high than normal temperature – fouled cooler tubes – cooling water temperature wrong –cooling water failure – defective control – heater control failure – internal fires – etc. | System
Less of | Temperature | Less/Low Temperature | Ambient conditions – reducing pressure – loss of heating – depressurisation of liquefied gas – Joule Thompson effect – line freezing – etc. | System
Level
More of | Level | More/ High Level | Outlet isolated or blocked – inflow greater than outflow – control failure – faulty level measurement – etc. | optional
Less of | Level | Less/ Low Level | Inlet flow stops – leak – outflow greater than inflow – control failure – faulty level measurement – draining of vessel – etc. | optional
Viscosity
More of | Viscosity | More Viscosity | incorrect material spec, temperature etc. | System
Less of | Viscosity | Less Viscosity | as above | System
Other Than
Composition Change |  |  | passing isolation valves, etc. | System
Contamination |  |  | wrong material, wrong operation, ingress of air, shutdown and start up conditions, etc. | System
Vent / Purge / Drain |  |  | Vent/ Purge / Drain of Toxic / Flammable | Vessel or unit
Start Up / Shut Down / Commissioning |  |  | Start Up / Shut Down / Commissioning Activities | Vessel or unit
Maintenance / Inspection |  |  | Maintenance / Inspection Activities | Vessel or unit
Leakage |  |  | From tube side to shell side of exchanger, roof drain leakage - etc. | Vessel or unit
Corrosion / Erosion |  |  | Corrosion / Erosion – Internal / External Corrosion at flare tips – etc. Internal/ external corrosion protection – engineering specifications – stress corrosion cracking – fluid velocities – etc. | Vessel or unit
Utilities Service Failure |  |  | Loss of electricity – instrument air – fuel gas – cooling water– steam – nitrogen – etc. | Vessel or unit
Maintenance Static |  |  | System drainage (how and where to) – isolation of equipment and prep for maintenance shutdown and start up (how) – etc. | Vessel or unit
Spare Equipment |  |  | Installed or not installed–Availability of spares –Modified specifications –Storage of spares – etc. | Vessel or unit
Reaction |  |  | Reaction by-products, missing reactions | Reactor or Unit
External Fire & Explosion |  |  | Adjacent facillity exposure from fire/explosion Lagging – firefighting –– safety showers – security –Adjacent facility exposures – etc. | Unit
Safety & Human Factor |  |  | Lagging, fire fighting, toxic gas, safety shower, hot/cold surface etc., security Hot work –Hot surfaces –Electrical classification –Auto-ignition or pyrophoric materials– etc. Safety for Operation & Ergonomic, Vehicles crash Feed stream impurities (e.g., mercury, H 2S, CO 2) –Dust generation–Powder handling– etc. Confined Space/ Escape & Evacuation/ Work at High Elevation & Dropped Object | Vessel or unit
Optional Guidewords
Instrumentation |  |  | Analyzer - flow measurement- location of instrumentation/alarm – indicators – recorders – etc. | Vessel or unit
Sampling |  |  | Sampling Point location, sampling point specification / feature, etc. | Vessel or unit
Phase |  |  | Phase change | optional
Traffic |  |  | Vehicles crash to equipment, unit | optional
Operations / Start Up / Shutdown |  |  | Purging – flushing – clearing blockages – steam out – start-up – normal shutdown – emergency shutdown – emergency operations – inspection of operating machines – guarding of machinery – etc. | optional
Maintenance / Inspection |  |  | Provision and adequacy for testing of equipment and product – location of sampling points – consistent philosophy –vibration detection – control separate from alarms – shutdowns – etc. | optional
Time |  |  | Too long–Too short –Wrong time– Time for analysis results – too soon– etc. | optional
Mixing |  |  | Fast mixing –Slow mixing–No mixing – etc. | optional
Information |  |  | Confusing – Inadequate – Missing –Misinterpreted – Partial–Stress –Wrong information– etc. | optional
Toxic |  |  | Feed stream impurities (e.g., mercury, H 2S, CO 2) –Dust generation–Powder handling– etc. | optional
Corrosive |  |  | Cathodic protection arrangements (internal and external) –Coating applications –Corrosion monitoring methods and –frequencies – Materials specification – Stress corrosion cracking – Fluid velocities –Sour service (e.g., H 2 S) –Riser splash zone– etc. | optional
Hot/ Cold Surface |  |  | Hot surfaces – Cold Surface | optional
Human Factor & Ergonomic |  |  | Access - Equipment Operation - Labelling– identification– instructions– training– qualifications– etc. | optional
Confined Space/ Escape & Evacuation/ Work at High Elevation & Dropped Object |  |  | Lift and manual handling, Work permit system, Rescue plan, Training | optional

## master (hidden)
(P/A/E/R/Q) | Risk Assessment Matrix (RAM)
P | People
A
E
R
Q

## HAZOP Worksheet Node (No.1)
HAZOP STUDY WORKSHEET
Project: | d1 | [8 empty] | NODE |  |  | Node1
Design Intent : | x | [8 empty] | System
x
Design Conditions: | [9 empty] | HAZOP Boundary
| x2 | [11 empty] | 18 Aug 2023
Operating Conditions:
PFD, PID No. : | [9 empty] | Date
Guide Word | Deviation | Causes | Consequences | CAT | Unmitigated Risk Assessment Matrix |  |  | Major Accident Event | Existing Safeguards | Mitigated Risk Assessment Matrix |  |  | Recommendations | Action No. | Action by
|  |  |  | (P/A/E/R/Q) | S | L | R | (Y/N) |  | S | L | R
Less/Low Flow | Less of | 1 | 11 | P | 5 | 4 | H | Y | e1 | 4 | 1 | H | r1 | Dungrat (TOP-XX)
MisdirectedFlow | Misdirected | 2 | 12 | A |  |  |  | N | e2 |  |  |  | r2 | TOP CMDP-Jaruwat P.
More/HighFlow | More of | 3 | 13 | E
No Flow | None | 4 | 14 | R
Reverse Flow | Reverse | 5 | 15 | Q
MLess/Low Pressure | Less of | 6 | 16 | P
More/High Pressure | More of | 7 | 17 | A
Note: